## Sheet1
Task | Estimated hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Total hours
Implement business class | 3 | Day 5: 2; Day 13: 1 | 2
Implement user account type enum | 1 | [14 empty] | 1 | bar: Day 2; Day 9 to Day 14
Implement booking class | 6 | Day 2: 1; Day 3: 2.5; Day 8: 2; Day 9: 1 | 3.5
Login functionality | 5 | [14 empty] | 0 | bar: Day 9 to Day 14
Write unit tests for sprint 2 & 3 functionality | 6 | [14 empty] | 0 | bar: Day 9 to Day 14
Homepage with login and signup | 3 | Day 5: 2; Day 6: 0.5
User dashboard | 6 | Day 6: 1; Day 10: 3; Day 13: 2; Day 14: 1 | 1
Actual remaining hours | 30 | 30 | 28 | 25.5 | 25.5 | 21.5 | 20 | 20 | 18 | 17 | 14 | 14 | 14 | 11 | 10 | 2.5
Estimated remaining hours | 30 | 27.8571 | 25.7143 | 23.5714 | 21.4286 | 19.2857 | 17.1429 | 15 | 12.8571 | 10.7143 | 8.5714 | 6.4286 | 4.2857 | 2.1429 | 0
[16 empty] | num days | 14