## Sheet1
Task | Estimated hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Total hours
Initialise Springboot Project | 2 | [8 empty] | 2 | bar: Day 1 to Day 2
Implement basic User API | 3 | Day 3: 3 | 3
Implement User class | 5 | [8 empty] | 2 | bar: Day 2; Day 5
Unit testing for Users | 5 | Day 8: 3 | 3
Acceptance Testing templates | 2 | Day 4: 0.5; Day 6: 1 | 1.5
Initialise React Project | 1 | [8 empty] | 1 | bar: Day 4
Actual remaining hours | 18 | 17 | 15 | 12 | 10.5 | 9.5 | 8.5 | 8.5 | 5.5
Estimated remaining hours | 18 | 15.75 | 13.5 | 11.25 | 9 | 6.75 | 4.5 | 2.25 | 0